## Skema 2020
Traffic planning principles, 2024 | [7 empty] | Version 17 af cin 25. nov. 2020
TIB | Line section | Total closure | Single track operation | Temporary Speed Restriction on neighboring track | Train paths per hour | Rerouting | Notes | 3rd party projects | Impact on traffic
1 | Copenhagen - Høje Taastrup (Høje Taastrup - Roskilde) | Max 4 weeks during general industrial holidays, or max 56 hours during weekends. Weekend total closures, only between Roskilde and Høje Taastrup, or in shade of other closures. | Can be planned during general industrial holidays in June-August, other holiday periods, or in shade of other closures. Only one track can be closed at a time between two locations with crossovers. The line section between Høje Taastrup and Roskilde has four tracks, so two tracks can be closed at the same time. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 6-8 train paths per hour. (14 if two out of four tracks are available between Roskilde - Høje Taastrup) | Trains can alternatively run via Vigerslev- Køge Nord - Ringsted. This requires ETCS-capable rolling stock. | Passengers can be rerouted on Metro trains between Copenhagen and Høje Taastrup. Total closures will be avoided between Høje Taastrup and Roskilde. In case of closure, some traffic can be rerouted through Vigerslev - Køge Nord - Ringsted, where closures cannot be planned at the same time. Large events, e.g., Roskilde Festival (ultimo June) are taken into consideration. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
1 | Roskilde - Ringsted | Max 4 weeks during general industrial holidays, or max 56 hours during weekends. Alternatively, in shade of other closures. | Can be planned during general industrial holidays in June-August, other holidays, or in shade of other closures. Only one track can be closed at a time between two locations with crossovers. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 6-8 train paths per hour. | Trains can alternatively run via Vigerslev- Køge Nord - Ringsted. This requires ETCS-capable rolling stock. | In case of closure, passengers to Viby and Borup are rerouted via bus. Freight traffic rerouted via Køge Nord. Large events, e.g., Roskilde Festival (ultimo June) are taken into consideration. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
1 | Ringsted - Korsør - Nyborg | 8 days and 8 hours during general industrial holidays, or max 30 hours during weekends. | Can be planned during general industrial holidays in June-August, other holidays, or in shade of other closures. Only one track can be closed at a time between two locations with crossovers. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 6-8 train paths per hour. (5 on the line section, Sorø - Slagelse) | No rerouting available. | In case of closure, freight traffic cannot pass through. As this line section has particularly high ridership, extra buses are required. Large events, e.g., Roskilde Festival (ultimo June) are taken into consideration. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
2 | Ringsted - Næstved | 8 days and 8 hours during general industrial holidays, or max 30 hours during weekends. | Can be planned during general industrial holidays in June-August, other holidays, or in shade of other closures. Only one track can be closed at a time between two locations with crossovers. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 6 train paths per hour. | There are limited options for rerouting via Roskilde - Køge, due to ERTMS. This option will gradually increase, as DSB-equipment is equipped with ERTMS. | Freight must be able to run between Ringsted - Næstved until their locomotives are equipped with ERTMS, allowing them to run via Roskilde - Køge - Næstved. DSB must have access to Næstved with their electric locomotives. Longer single-track operations are allowed, as well as total closures in case of rerouting. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
2 | Næstved - Rødby Færge | Total closures are given to the RFB project until 2022 (K23), as agreed upon. | Single track operation is given to the RFB-project until 2022 (K23), as agreed upon. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | At least 6 train paths per hour between Ringsted and Vordingborg. | Traffic can be rerouted via Roskilde - Køge, with trains equipped with ERTMS-equipment. Between Køge - Næstved, ATC is used. | RFB coordinates the works on TIB-2, including the work on SP and EP. Lokaltog must be able to get to Nykøbing F. with their customers outside of holiday periods. Currently, there is a lack of clarification regarding traffic before SP. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low
5 | Roskilde - Holbæk | Total closures must be held during the general industrial holidays (week 27-32). | Closures on Roskilde - Holbæk should be planned around public holidays, or the general industrial holidays. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | At least 6 train paths per hour. | No rerouting available. | Lokaltog have trains running between Holbæk - Tølløse. Total closures cannot be done in a way so the customer cannot get to their workshop in Holbæk - otherwise, this must be agreed upon with Lokaltog. DSB has previously ran their IC trains through Tølløsebanen, when there has been single track operations on TIB-1 between Ringsted - Korsør. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
5 | Holbæk - Kalundborg | Total closures can be planned all year. | Total closures can be planned throughout the year. However, closures should be planned in a way that only one part of the section is closed at a time, e.g. Jyllinge - Kalundborg. | Speed restrictions should allow for the highest possible speed. | At least 4 train paths per hour during rush hour. Alternatively, 2 train paths per hour outside of rush hour. | No rerouting available. | This section must not have a total closure, at the same time as Holbæk - Roskilde. DSB has to be able to service their trains, if this is located between Holbæk and Kalundborg. This can also impact the duration of a total closure between Roskilde and Holbæk. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low
6 | Vigerslev-Køge Nord-Ringsted | Only in the evenings, or at night. | Only in the evenings, or at night. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 6-8 train paths per hour. | Alternatively, trains can run through Høje Taastrup - Roskilde. Once SP has been rolled out, trains can be rerouted to Køge and Næstved from Køge Nord. | As the line has opened recently, only evening/night maintenance closures are expected. Closures cannot be planned on this line section, if there are planned closures on the line from Copenhagen - Roskilde - Ringsted. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
10 | Elsinore - Copenhagen | Max 6 weeks during general industrial holidays. | Can be planned during general industrial holidays (week 27-32) between Østerport- Nivå, and Snekkersten - Elsinore. Between Nivå - Snekkersten, closures can be planned at other times of the year. Single track operations can also be carried out in connection with public holiday periods. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | At least 6 train paths per hour. (Between Nivå and Snekkersten, less than 6). | No rerouting available. | Trains are reversed in Nivå between Østerport - Nivå. Both Lokalbanen and DSB operate between Snekkersten - Elsinore. Freight runs 2-3 times a week between Østerport - Snekkersten - Elsinore, and on to the tracks that are managed by Lokalbanen. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
11 | Peberholm - Kbh/Vigerslev | 8 days and 8 hours during general industrial holidays, or max 30 hours during weekends. | Can be planned during general industrial holidays in June-August, other holidays, or in shade of other closures. Only one track can be closed at a time between two locations with crossovers. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 6-8 train paths per hour. | No rerouting opportunites. A total closure of this section closes the ScanMed corridor. No passenger traffic. | In case of closure, freight traffic cannot pass through. Passengers can travel by the Metro between Copenhagen City and the airport. Total closures should not exceed 8 days per year. Large events, e.g., Roskilde Festival (ultimo June) are taken into consideration when planning closures. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
1 + 23 | Snoghøj - (Fredericia) - Skanderborg | 8 days and 8 hours during general industrial holidays, or max 30-56 hours during weekends. | Single-track operation in May-September, or during holiday periods. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 4 train paths per hour. | Trains can be rerouted in the triangle area Snoghøj - Taulov - Fredericia. | If Snoghøj - Fredericia is closed, trains must be reversed in Taulov. If Taulov - Snoghøj is closed, trains must be reversed in Fredericia. There must be at least 6 train paths between Fredericia - Vejle. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
23 | Skanderborg-Aarhus | 8 days and 8 hours during general industrial holidays, or max 30-56 hours during weekends. | Single track operation in June-August, or during holiday periods. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 4-6 train paths per hour. | No rerouting available. | There must be 4-6 train paths per hour between Skanderborg - Aarhus, as several railway companies operate on this line section. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
24 | Aarhus - Aalborg | 8 days and 8 hours during general industrial holidays, or max 30-56 hours during weekends. | Single-track operation in May-September, or during holiday periods. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | At least 4 train paths per hour. | No rerouting available. | There is the possibility of a long rerouting through Langå - Struer - Skanderborg. From a Traffic point of view, this is not an option. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
1 + 26 | Nyborg - (Snoghøj) - Lundeskov | 8 days and 8 hours during general industrial holidays, or max 30 hours during weekends. | Can be planned during general industrial holidays in June-August, other holidays, or in shade of other closures. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | 6 train paths per hour. | No rerouting available between Nyborg - Snoghøj. | Freight cannot get through. Extra buses required for passenger traffic, as this is the most busy line section in Denmark. Large events, e.g., Roskilde Festival (ultimo June) are taken into consideration. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
26 | Lunderskov - (Tinglev) - Padborg | 8 days and 8 hours during general industrial holidays, or max 30 hours during weekends. | Single track operation in June-August, or during holiday periods. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | At least 4 train paths per hour. | No rerouting available to Padborg. Trains can, however, be rerouted through Esbjerg to Tønder/Nïebüll, when track closure south of Lunderskov. | Rerouting freight through Tønder/Nïebüll is more costly, and this line section cannot guarantee the agreed upon train lengths. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
29 | Bramming - Esbjerg | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. | Single track operation in June-August, or during holiday periods. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | At least 4 train paths per hour. | No rerouting available. | There are many travelers and several train systems between Bramming and Esbjerg, including an Intercity system. There are freight transports. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
29 | Lunderskov - Bramming | Total closures can be planned throughout the year. See "Notes". | Single-track operation in May-September, or during holiday periods. | Always at least 80 km/h on neighboring track. In case of a speed restriction of 40 km/h, this must be planned as a complete line closure, or during week 27-32, or other holidays. | At least 4 train paths per hour. | No rerouting available. | This stretch cannot be closed at the same time as Lunderskov - Padborg. Total closures should be as brief as possible. Planning should consider the summer holidays, as IC trains and freight trains are in use. Total closures must be short, and shaded by other works. There are IC trains and freight. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low
4 | Roskilde - Køge - Næstved | Total closures planned in industrial holidays, as well as school holidays. Maximum duration of 4 weeks. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must take the number of train paths per hour into consideration. A speed restrictions of 40 km/h should not be the case on more than one speed restriction on the section. | At least 2 train paths per hour. | Trains can run via Ringsted to Roskilde. Once SP has been rolled out on TIB-6, trains can run from Køge to Køge Nord. | The rerouting option via Ringsted is only for "materieltog". Lokaltog runs between Roskilde and Køge (ETCS section). DSB runs between Køge and Næstved. The autumn holidays can be used for various closures from Monday to Friday. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
21 | Odense - Ringe | Total closures must be planned in week 29-31 and have a max duration of 14 days, or in weekends with a max duration of 56 hours. The same applies for public holidays and school holidays. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must take the number of train paths per hour into consideration. A speed restrictions of 40 km/h should not be the case on more than one speed restriction on the section. | At least 4 train paths per hour. | No rerouting available. | If Odense - Ringe is closed, the entire line can be closed. Closures on stations with one track can cause less train paths per hour. It is not possible to plan closures in the summer holidays several years in a row. Banedanmark has to plan concurrent works to ensure that there is no need for closures every year. Special consideration must be given to passengers to and from Odense Hospital. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
21 | Ringe - Svendborg | Total closures must be planned in the summer holidays, weeks 27-32, and have a max duration of 4 weeks, or in weekends with a max duration of 56 hours. The same applies for public holidays and school holidays. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must take the number of train paths per hour into consideration. A speed restrictions of 40 km/h should not be the case on more than one speed restriction on the section. | At least 2 train paths per hour. | No rerouting available. | Closures on stations with one track can cause less train paths per hour. Total closures can be planned on special occasions. If Odense - Ringe is closed, Ringe - Svendborg must be closed at the same time. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
25 | Aalborg - Hjørring | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. Max 4 weeks. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. See "Notes". | At least 80 km/h on neighboring track on the line section Aalborg - Lindholm. Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 4 train paths pr. hour between Aalborg - Lindholm. | No rerouting available. | Closures on the line section Aalborg - Lindholm - Aalborg Airport should be planned with respects to when the largest number of people are expected to travel here. Nordjyske must be able to get to their workshop in Hjørring. Freight transports are planned to Hirtshals, which is crucial for placement of closures. The autumn holiday can be used for various closures Monday-Friday. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
25 | Hjørring - Frederikshavn | Total closures can be planned throughout the year. See "Notes". Max 4-6 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | No rerouting available. | Nordjyske Jernbaner must be able to reach their workshops in Skagen or Hjørring. Closures and length of closure must reflect this consideration. Closures should be placed outside of the summer holidays, in consideration of the holiday visitors. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low
28 | Tinglev - Sønderborg | Total closures can be planned throughout the year. See "Notes". Max 6 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | No rerouting available. | Closures must be planned so that as many works as possible is done simultaneously, to minimize the risk of BDK having to return immediately. Closures can thus be performed for up to 3 months at a time. Via communication with RUs, we must be able to perform closures outside school holidays. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low
30 | (Esbjerg) Bramming - Ribe | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. Max 4 weeks. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | No rerouting available. | There are many students traveling between Ribe and Esbjerg. When Bramming - Niebüll is closed, Lunderskov - Padborg cannot be closed at the same time. The autumn holidays can be used for various closures from Monday to Friday. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
30 | Ribe - Tønder | Total closures can be planned throughout the year. See "Notes". Max 6 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | No rerouting available. | When Bramming - Niebüll is closed, Lunderskov - Padborg cannot be closed at the same time. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | low
31 | Esbjerg - Varde | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. Max 4 weeks. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | There is rerouting available, but this is considered to not be a viable option due to the added time required. | Go Collective must be able to get to their workshop in Varde. Special consideration must be paid to military transports to/from Oksbøl/Varde, so that Varde cannot have a total closure, unless this is shadowing other total closures. The autumn holidays can be used for various closures from Monday to Friday. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
31 | Varde - Holstebro | Total closures can be planned throughout the year. See "Notes". Max 6 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | There is rerouting available, but this is considered to not be a viable option due to the added time required. | Go Collective must be able to get to their workshop in Varde. Special consideration must be paid to military transports to/from Oksbøl/Varde, so that Varde cannot have a total closure, unless this is shadowing other total closures. The autumn holidays can be used for various closures from Monday to Friday. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | low
32 | Langå - Viborg | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. Max 4 weeks. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | There is rerouting available, but this is considered to not be a viable option due to the added time required. | There are several train systems, and lots of customers. Special attention must be given to military transport to/from Skive. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
32 | Viborg - Struer | Total closures can be planned throughout the year. See "Notes". Max 6 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | There is rerouting available, but this is considered to not be a viable option due to the added time required. | This line section cannot have a closure at the same time as the line section between Struer - Herning. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low
33 | Vejle - Herning | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. Max 4 weeks. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | There is rerouting available, but this is considered to not be a viable option due to the added time required. | There are several train systems, and lots of customers. The autumn holidays can be used for closures from Monday - Friday. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
33 | Herning - Holstebro - Struer | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. Max 4 weeks. | 6-9 hours of closure. Can be performed in Mid June-Mid August, or during holiday periods. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | There is rerouting available, but this is considered to not be a viable option due to the added time required. | Closures between Herning and Skibbild must be done in shorter periods, because of the Superhospital in Gødstrup. There are many student travelers between Holstebro and Struer. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Medium
34 | Struer - Thisted | Total closures can be planned throughout the year. See "Notes". Max 6 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | Ingen bemærkninger | No rerouting available. | Replacement buses are a viable alternative in case of closures. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low
35 | Skanderborg - Herning | Total closures must be placed in the general industrial holidays (week 28-31), other public holidays, or max 30-56 hours during weekends. Max 4 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | At least 2 train paths per hour. | There is rerouting available, but this is considered to not be a viable option due to the added time required. | Extra train systems are in use, and the customer base is large. In case of closures, trains must be able to run to/from Silkeborg. The autumn holiday can be used for various closures from Monday-Friday. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | High
35 | Herning - Skjern | Total closures can be planned throughout the year. See "Notes". Max 4 weeks. | 6-9 hours of closure, all year. | Speed restrictions must be aligned with the number of train channels per hour. In case of several restrictions on the line section, speed restrictions of 40 km/h should not occur. | Ingen bemærkninger | There is rerouting available, but this is considered to not be a viable option due to the added time required. | Replacement buses can be used on this section in case of closures. | Projects are judged by size and importance, as well as the possibility for the project to be in shade of other closures. | Low

## Supp. tekst
En TIB strækning gælder både stationer og strækninger | When having a total closure on the RFC from Sweden to Germany, closures must be coordinated. When requesting a total closure, an alternative must always be presented, that - if at all possible - does not include a total closure. On the section from Ringsted to Padborg, a maximum of 8,33 days of total closure in a year. | Double left = 30 hours in a weekend. | If there are more closures the same year on one TIB-section, there can only be a maximum of the number of days/weeks specified. As an example, look to TIB-1, which can have a maximum of 4 weeks of total closure in a year. | Speed restrictions are adjusted - might only be the case in nights. The length of speed restrictions of 40 km/h must be adjusted based on the number of train paths. That means that the speed restrictions will only be between 300 and 500 meters. | The document has been created so that the stations and sections with most trains, most passengers, most railway undertakings, lack of rerouting, as well as any section on the transit corridor is marked by red, indiciating high impact. | Based on the document, there will be cases, where the projects must be placed differently to accommodate durations, times and speed restrictions. | Trafik has to create a group with representatives from freight undertakings and passenger undertakings, where information can be had on changes and new runs. This information must be given at the beginning of Q4. | When Banedanmark makes closures of 4-6 weeks, or there is a need for longer closures with regards to single-tracked sections, it has to be planned with more concurrent works, so that a total closure is not necessary for the next 10 years. This means that works that could wait, have to be pushed forward.